## Summary
GRPS - Dickinson Elementary, Cesar E Chavez Elementary, and Kent Hills Elementary combined project
#REF!
NAME OF CM FIRM
| GPRS Combined Program Value: | 5800000
| ESTIMATED COST OF CONSTRUCTION WORK: | 1200000 | Dickinson
|  | 800000 | Cesar Chavez
|  | 2600000 | Kent Hills
| CONSTRUCTION DELIVERY METHOD: | CMc | Construction Manager as Constructor
|  | Preconstruction |  | Construction |  |  |  |  | CMc | Construction Manager as Constructor
| START DATE: | 2025-02-01 |  | 2025-05-01 |  | * assume on site work summer 2025 & 2026 |  |  | CMa | Construction Manager as Advisor
| FINISH DATE: | 2025-05-01 |  | 2026-08-01 |  | dependent upon component lead times |  |  | DB | Design-Build, with GMP or Cost plus a Fee
[9 empty] | GC | General Contractor, with GMP or Cost plus a Fee
|  |  | Months | Weeks | Days |  |  |  | TBD | To be Determined
| PROJECT DURATION: | Pre-construction | 2.9667 | 12.7143 | 89
|  | Construction | 15.2333 | 65.2857 | 457
| ESTIMATED BUILDING AREA SF: | 26000 |  | Dickinson
|  |  | 30000 | Cesar Chavez
|  |  | 54500 | Kent Hills
GENERAL CONDITIONS RECAP SUMMARY
[5 empty] | EQ. & MATL. | LABOR | SUB-CON | TOTAL
| DESCRIPTION |  |  |  | TOTAL | TOTAL | TOTAL | COST
| PRECONSTRUCTION SERVICES |  |  |  | 0 | 200 | 0 | 200
| PRECONSTRUCTION SERVICES REIMBURSABLE EXPENSES |  |  |  | 0 |  | 0 | 0
| CONSTRUCTION PERSONNEL |  |  |  | 0 | 200 | 0 | 200
| CM REIMBURSABLES |  |  |  | 240 | 0 | 0 | 240
| PERMITS, INSURANCE & TAXES |  |  |  | 10 | 0 | 0 | 10
| TOTAL GENERAL CONDITIONS |  |  |  | 250 | 400 | 0 | 650
[7 empty] | GENERAL CONDITIONS AS % OF CONSTRUCTION COST = | 0.05417%
CONSTRUCTION MANAGER'S OVERHEAD & PROFIT (%) =
| Alternate Add: | 0 | Project Managed Under Prevailing Wage Rules
[7 empty] | Preconstruction Hours: | 20
[7 empty] | Construction Hours: | 20
[7 empty] | TOTAL ESTIMATED CONSTRUCTION SERVICES AS % OF CONSTRUCTION COST = | 0.05417%
[7 empty] | TOTAL ESTIMATED CONSTRUCTION SERVICES COST = | 2491.6667
NOTES:
1. Personnel rates include the salaries of personnel and the portion of the cost of their mandatory and customary contributions and benefits related thereto, such as employment taxes and other statutory employee benefits, insurance, sick leave, holidays, vacations, pensions, and similar contributions and benefits. 2. Personnel rate increases are limited to three (3%) percent per year, after 12/31/2025. Hourly Rates shall be based on a forty (40) hour work week/salaried position and while the Construction Manager’s Personnel may work overtime, the Owner shall never be charged overtime rates. 3. General Liability Insurance may only be applied to Construction Manager’s Fee, and not the Cost of the Work

## Staff Hours
NAME OF CM FIRM | 0
Populate all staff and associated rates you intend to charge to the project. Add any staff you intend to charge.
SUMMARY OF STAFF HOURS
| Project Month (Overall) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
|  |  | 2024 | [5 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
|  |  | 2024-07-02 | 2024-08-02 | 2024-09-02 | 2024-10-02 | 2024-11-02 | 2024-12-02 | 2025-01-02 | 2025-02-02 | 2025-03-02 | 2025-04-03 | 2025-05-04 | 2025-06-05 | 2025-07-06 | 2025-08-07 | 2025-09-08 | 2025-10-09 | 2025-11-10 | 2025-12-11 | 2026-01-02 | 2026-02-02 | 2026-03-02 | 2026-04-03 | 2026-05-04 | 2026-06-05 | 2026-07-06 | 2026-08-06 | 2026-09-06 | 2026-10-06 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01
|  |  | 2024-07-02: Pre-Construction Phase Project Hours | Pre-Construction
Personnel/Name | Function | Hourly Rate | [40 empty] | Hours | Cost
| Project Exec. | 0 | [40 empty] | 0 | 0
Joe 'Example' Dirt | Sr. Proj. Mgr. | 10 | [40 empty] | 20 | 200 | bar: 2024-07-02 to 2027-10-01
| Proj. Mgr. 1 | 0 | [40 empty] | 0 | 0
| Pre-Con Mgr. | 0 | [40 empty] | 0 | 0
| Sr. Estimator | 0 | [40 empty] | 0 | 0
| Estimator 1 | 0 | [40 empty] | 0 | 0
| Mech. Est. | 0 | [40 empty] | 0 | 0
| Elect. Est. | 0 | [40 empty] | 0 | 0
| Scheduler | 0 | [40 empty] | 0 | 0
| Proj. Supt. | 0 | [40 empty] | 0 | 0
| Accountant | 0 | [40 empty] | 0 | 0
| Admin. Asst. | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
| Pre-Construction Hours: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 200
Construction Months
|  |  | 2024-07-02: Construction Phase Project Hours | Construction
Personnel/Name | Function | Hourly Rate | [40 empty] | Hours | Cost
| Project Exec. | 0 | [40 empty] | 0 | 0
Joe 'Example' Dirt | Sr. Proj. Mgr. | 10 | [40 empty] | 20 | 200 | bar: 2025-02-02 to 2026-09-06
| Proj. Mgr. 1 | 0 | [40 empty] | 0 | 0
| Proj. Mgr. 2 | 0 | [40 empty] | 0 | 0
| Proj. Mgr. 3 | 0 | [40 empty] | 0 | 0
| Proj. Mgr. 4 | 0 | [40 empty] | 0 | 0
| Proj. Engr. 1 | 0 | [40 empty] | 0 | 0
| Proj. Engr. 2 | 0 | [40 empty] | 0 | 0
| Proj. Engr. 3 | 0 | [40 empty] | 0 | 0
| Proj. Engr. 4 | 0 | [40 empty] | 0 | 0
| Safety Engr. | 0 | [40 empty] | 0 | 0
| General Supt. | 0 | [40 empty] | 0 | 0
| Proj. Supt. 1 | 0 | [40 empty] | 0 | 0
| Proj. Supt. 2 | 0 | [40 empty] | 0 | 0
| Proj. Supt. 3 | 0 | [40 empty] | 0 | 0
| Proj. Supt. 4 | 0 | [40 empty] | 0 | 0
| Accountant | 0 | [40 empty] | 0 | 0
| Admin. Asst. | 0 | [40 empty] | 0 | 0
| Expeditor | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
| Construction Hours: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 200

## Construction Support
|  | NAME OF CM FIRM | 0
|  |  | Preconstruction |  | Construction
|  | START DATE: | 2025-02-01 |  | 2025-05-01
|  | FINISH DATE: | 2025-05-01 |  | 2026-08-01
Populate all categories you intend to charge to the project. Add any other costs you intend to charge.
|  |  |  | Months | Weeks | Days
|  | PROJECT DURATION: | Pre-construction | 2.9667 | 12.7143 | 89
|  |  | Construction | 15.2333 | 65.2857 | 457
| CODE | DESCRIPTION | QTY. | UNIT | UNIT | (E) EQUIP. & |  | (S) SUB- | TOTAL
| NO. |  |  |  | PRICE | MAT'L | (L) LABOR | CONTRACTOR | COST
CM REIMBURSABLES
E |  | PROJECT OFFICE 1 |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | PROJECT OFFICE 2 | 24 | MO | 10 | 240 | 0 | 0 | 240 | TRUE
E |  | ARCHITECT-OWNER OFFICE |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | TRADES TRAILER |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | TOOL/STORAGE TRAILER |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | STORAGE RENTAL |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | JOB SET-UP/REMOVAL - 1 |  | LS |  | 0 | 0 | 0 | 0 | TRUE
E |  | JOB SET-UP/REMOVAL - 2 |  | LS |  | 0 | 0 | 0 | 0 | TRUE
E |  | TEMPORARY TOILETS - 1 |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | TEMPORARY TOILETS - 2 |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | OFFICE FURNITURE - 1 Not an allowable reimbursement |  |  |  | 0 | 0 | 0 | 0 | TRUE
E |  | OFFICE FURNITURE - 2 Not an allowable reimbursement |  |  |  | 0 | 0 | 0 | 0 | TRUE
E |  | OFFICE EQUIPMENT - FAX/Copy - 1 |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | OFFICE EQUIPMENT - FAX/Copy - 2 |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | Software license monthly |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | Site network/internet monthly |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | OFFICE SUPPLIES - 1 - Not an allowed reimbursement |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | OFFICE SUPPLIES - 2 - Not an allowed reimbursement |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | TELEPHONE - 1 |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | TELEPHONE - 2 |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | POSTAGE & EXPRESS - 1 |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | POSTAGE & EXPRESS - 2 |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | JOB SITE RADIO/NEXTEL |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | OFFICE ELECTRIC - 1 |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | OFFICE ELECTRIC - 2 |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | OFFICE FUEL - 1 |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | OFFICE FUEL - 2 |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | OFFICE PLUMBING |  | LS |  | 0 | 0 | 0 | 0 | TRUE
[6 empty] | 0 | 0 | 0 | 0 | TRUE
[6 empty] | 0 | 0 | 0 | 0 | TRUE
[6 empty] | 0 | 0 | 0 | 0 | TRUE
[6 empty] | 0 | 0 | 0 | 0 | TRUE
[6 empty] | 0 | 0 | 0 | 0 | TRUE
[6 empty] | 0 | 0 | 0 | 0 | TRUE
[6 empty] | 0 | 0 | 0 | 0 | TRUE
[6 empty] | 0 | 0 | 0 | 0 | TRUE
|  | CM REIMBURSABLES TOTAL |  |  |  | 240 | 0 | 0 | 240
PERMITS, INSURANCE & TAXES
E |  | BUILDING PERMIT - by CM | 1 | LS | 10 | 10 | 0 | 0 | 10 | TRUE
E |  | SPECIAL PERMITS - by CM |  | LS |  | 0 | 0 | 0 | 0 | TRUE
E |  | SPECIAL FEES - by Owner |  | LS |  | 0 | 0 | 0 | 0 | TRUE
E |  | SITE PLAN REVIEW - by Owner |  | LS |  | 0 | 0 | 0 | 0 | TRUE
E |  | BUILDERS RISK INSURANCE |  | LS |  | 0 | 0 | 0 | 0 | TRUE
E |  | GENERAL LIABILITY INSURANCE |  | LS |  | 0 | 0 | 0 | 0 | TRUE
|  | PERMITS, INSURANCE & TAXES TOTAL |  |  |  | 10 | 0 | 0 | 10
SUMMARY & ERROR CHECK
|  | LABOR SUBTOTAL: | 0 | TRUE
|  | TOTAL: | 250 | FALSE

## Staff Cashflow
NAME OF CM FIRM | 0
STAFFING CASHFLOW
| Project Month (Overall) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
|  |  | 2024 | [11 empty] | 2025
|  |  | 2024-01-20 | 2024-02-20 | 2024-03-20 | 2024-04-20 | 2024-05-20 | 2024-06-20 | 2024-07-20 | 2024-08-20 | 2024-09-20 | 2024-10-20 | 2024-11-20 | 2024-12-20 | 2025-01-20 | 2025-02-20 | 2025-03-20
|  |  | 2024-01-20: Pre-Construction Phase Project Hours | [10 empty] | Pre-Construction
Personnel | Function | Hrly Rate | [25 empty] | Hours | Cost
0 | Project Exec. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Joe 'Example' Dirt | Sr. Proj. Mgr. | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 20 | 200
0 | Proj. Mgr. 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Pre-Con Mgr. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Sr. Estimator | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Estimator 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Mech. Est. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Elect. Est. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Scheduler | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Supt. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Accountant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Admin. Asst. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pre-Con Staff Costs: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 20 | 200
Construction Months
|  |  | 2024-01-20: Construction Phase Project Hours | [10 empty] | Construction
Personnel | Function | Hrly Rate | [25 empty] | Hours | Cost
0 | Project Exec. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Joe 'Example' Dirt | Sr. Proj. Mgr. | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 20 | 200
0 | Proj. Mgr. 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Mgr. 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Mgr. 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Mgr. 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Engr. 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Engr. 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Engr. 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Engr. 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Safety Engr. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | General Supt. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Supt. 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Supt. 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Supt. 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Supt. 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Accountant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Admin. Asst. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Expeditor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction Staff Costs: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 20 | 200
| Staff Cost Cashflow: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0 | 40 | 400